## Timeline
| Kantima Pinthong | Inkspire - A Writing Assistant Web Application | Total Hours: | 204 | x Hourly rate: | 35
Week | Title | Description | Difficulty | Est. Hours
1 | Complete Requirements Document | Finalize the Introduction, Content, Functionality, Technical, Data Design, Dataflows, Wireframes, Development Specifications, and Conclusion. Review all Must/Should/Nice features for consistency. | Medium | 12 | Labour Cost: | 7140
| Finalize wireframes | Complete low-fidelity wireframes for authentication, Idea Vault, My Stories, Story Workspace, Characters, Timeline, Story Builder, World Builder, Writing, Story Check, and status messages. | Medium | 5
| Database requirements | Confirm the data collected by each feature and list the main tables, required fields, primary keys, and relationships needed for the application. | Medium | 5
| User stories and CRUD coverage | Check that the Must Have and Should Have user stories cover Create, Read, Update, and Delete actions where required, including success and error states. | Medium | 6
2 | Create React and Node/Express project structure | Set up the React frontend and Node.js/Express backend, organize folders, configure the REST API structure, and confirm the application runs locally. | Medium | 6
| Create PostgreSQL database | Create the online PostgreSQL database and configure the backend connection. | Medium | 5
| Build primary database tables | Create and test the main tables for users, ideas, stories, characters, timeline events, chapters, scenes, checklists, locations, drafts, research, and relationships. | Hard | 8
| Set up shared layout and navigation | Build the main layout, navigation, Story Workspace navigation, and basic responsive structure used across the application. | Medium | 5
3 | Implement user registration | Create the Writer registration form, store account information securely, validate required fields, and display validation messages. | Medium | 6
| Implement login and logout | Build login and logout functionality and protect private Writer pages and story data. | Medium | 5
| Build Idea Vault CRUD | Create, read, update, and delete story ideas with required-field validation, delete confirmation, and success/error messages. | Hard | 10
| Develop an idea into a story | Allow a Writer to select an Idea Vault item and create a My Story from it while keeping the original idea available. | Hard | 6
| Build My Stories CRUD and Story Overview | Create, read, update, and delete stories and display the selected story's title, genre, synopsis, and basic story information. | Hard | 7
4 | Build Character Studio CRUD | Create, read, update, and delete characters within the selected story and store each character with the correct StoryID. | Hard | 8
| Build Story Timeline CRUD | Create, read, update, and delete timeline events within the selected story and display them in a clear timeline view. | Hard | 7
| Build Story Builder CRUD | Create the Chapter and Scene structure and allow the Writer to add, edit, organize, and delete each level within the selected story. | Hard | 8
| Build World Builder CRUD | Create, read, update, and delete locations and basic world information within the selected story. | Hard | 6
| Run initial user testing | Test the main Writer workflow with sample users, observe usability issues, record feedback, and identify changes needed before continuing development. | Medium | 5
5 | Fix issues from user testing | Make small usability and workflow improvements based on the user testing results. | Medium | 5
| Build Writing Editor | Create the chapter/scene writing page with a basic Rich Text Editor and controls for saving and editing draft content. | Hard | 10
| Save and reopen online drafts | Store chapter and scene drafts in the online PostgreSQL database and test that saved writing can be reopened later and from another device/browser. | Medium | 7
| Build Story Structure Checklist | Allow the Writer to create, edit, delete, view, and manually mark chapter planning items as complete. | Hard | 6
| Build Story Check | Create the Story Check page showing relevant characters and locations for the selected chapter, along with the Writer's Story Structure checklist. | Hard | 7
| Add save and validation states | Add clear success, error, and status messages for important save, update, delete, and required-field actions. | Medium | 4
6 | Build Research Vault & Notes | Create, read, update, and delete research records, notes, and reference links associated with the selected story. | Medium | 4
4 | Build Relationship Map | Store character relationships and display them as a simple visual relationship map for the selected story. | Hard | 5
| Build Share Chapter / Scene | Allow a Writer to create and disable a read-only share link for a selected chapter or scene. | Hard | 5
| Build Reviewer View | Create the read-only page opened by a valid shared link and test chapter/scene sharing and full-story sharing. | Medium | 5
| Deploy the application online | Deploy the React frontend, Node.js/Express backend, and PostgreSQL database to the selected cloud hosting environment and confirm the deployed application works. | Medium | 3
7 | Run final functional and CRUD testing | Test the completed Must Have and Should Have features, including Create, Read, Update, Delete, validation, permissions, and success/error states. | Hard | 6
| Run story data isolation tests | Use at least two test stories to verify that characters, timeline events, locations, chapters, scenes, drafts, and other story data remain connected to the correct story. | Hard | 6
| Run responsive and accessibility checks | Test desktop and mobile layouts, keyboard navigation, labels, required fields, readable text, and basic accessibility requirements. | Medium | 5
| Final documentation and demonstration presentation | Update the Document with final decisions, record technical information, prepare final documentation, and prepare the project for demonstration. | Medium | 6
Note on B2: SWD: What are the tasks you plan to work on during this week?
Note on C2: SWD: A brief description of the tasks for this component.
Note on D2: SWD: What is your perception of how difficult this component will be? Easy ¦ Medium ¦ Difficult
Note on E2: SWD: How many hours will it take to complete this task (include 3hours "client" meeting time in your overall weekly estimates)?